## Slide 1: County Service Area Zones of Benefit Special Tax Election Schedule and Calendar
Notes: This presentation was initially included in the annual Zone of Benefit Advisory Committee training session held November 16, 2006. It has been modified slightly as staff has received additional information regarding the processes. Originally compiled by Department of Transportation Staff: Michele Smith, Administrative Services Officer and Elizabeth Zangari, Department Analyst.

## Slide 2: Elections: Landmark Dates
1985 - Policy and Procedure Guidelines adopted by County Board of Supervisors.
December 27, 1994 – Charter for El Dorado County becomes effective.
November 6, 1996 – Proposition 218 becomes Articles 13C and 13D of the California State Constitution.
  13C: Special Taxes
  13D: Benefit Assessments
Notes: The County Charter added voter approval for any new assessments or taxes and for any increases to existing assessments or taxes. Prop 218 made a distinction in approval processes between special taxes and benefit assessments. Any new assessments or taxes imposed between January 1, 1996 and November 6, 1996 not already approved by voters were subject to election within two years – by November 6, 1998.

## Slide 3: Elections: Zone Funding Then and Now
Circa 1980’s
Concurrence of Property Owners set amount.
Advisory Committee recommends amount.
Board of Supervisors approved and set.
Now: 1995 to present
Any increase or change in methodology requires approval through some sort of proceeding.
Distinction among General Tax, Special Tax, Benefit Assessment, Service Charges.
Notes: Both the County Charter and “Prop 218” had significant impact on the zones of benefit by eliminating the ability of the Advisory Committees to independently recommend the assessment or tax amount for any given year.

## Slide 4: Elections: Special Tax v. Benefit Assessments
Special Tax
Projected costs vs. projected revenue can provide basis.
Is uniformly applied to each parcel*.
Requires approval of two-thirds majority of registered voters in zone.
Conducted by Registrar of Voters (Elections Department)
*(Except that unimproved parcels may be taxed at a lower rate than improved parcels).
Benefit Assessment
Engineer’s report required for basis (Nexus).
Varies among parcels by value of benefit derived.
Requires approval of weighted majority of property owners in the zone.
Open ballot at Public Hearing of Board of Supervisors.
Notes: Summary:
Significant changes to state and County code that have occurred since the majority of the road maintenance zones of benefit were formed have impacted the establishment of and increase to revenue sources. The processes for setting both the special tax and benefit assessments have advantages and disadvantages. Ultimately, the zone residents and advisory committees must weigh these issues, and recommend which process they find to be in the better interest of their particular zone to zone administration staff for presenting before the Board of Supervisors.
This presentation focuses on Special Taxes.
Further questions regarding these processes may be directed to Zone of Benefit Administration.

## Slide 5: Elections: Chain of Events
Advisory Committee requests Election
County Zone Administration prepares
  Schedule with Elections and Board of Supervisors
  Resolution with Ballot Question
  Board of Supervisors Agenda Item
Board of Supervisors Adopts Resolution
  Setting the Election Date
  Instructing Registrar of Voters to Conduct
Election Department conducts election
Special Tax placed on Tax Roll the following August 10.
Notes: To project availability of a new or increased special tax, work back from the tax roll deadline: August 10.

## Slide 6: The Calendars
Zone Meeting Schedule
    Policy & Procedure Guidelines
Delivery of Tax Rolls
    Tax and Revenue Code
Mailed Ballot Election Calendar
    Elections Code
    Elections Department Administrative Calendar
Board of Supervisors Agenda Calendar
    Board sets annually
Notes: Zone advisory committees are required to meet four (4) times each year. Tax rolls are delivered August 10 each year.

## Slide 7: The Calendar: Zone Meeting
Notice and Agenda for General Meeting
  Notice must include the agenda.
  Specifically address the topic, for example “Propose $50 increase to special tax amount.”
Minutes of the Meeting
The Advisory Committee’s recommendation:
  Recommending the special tax amount.
  Requesting the election.
Notes: The Board recently indicated concerns regarding compliance with the Brown Act when advisory committees made requests to initiate proceedings to increase a special tax. Staff was directed to reiterate and document the noticing and meeting requirements prior to initiating subsequent special tax elections.
The description of an agenda item must be clear. Phrases like “Review of funding” or “Potential for election” do not adequately address a committee’s request to the County to increase (or adopt) a special tax for the zone.

## Slide 8: The Calendar: Tax Roll Dates
State deadline for Direct Charges on the Tax Roll:
          August 10th each year
Tax Roll is set and billed annually
  Installments are due December 10 and April 10.
Changes must be approved before August 10th to be included on the tax roll for the upcoming year.
Notes: Tax rolls are set by the Property Tax Division of the County Auditor-Controller’s Office. Zone Administration staff delivers the Direct Charges to the Auditor’s Office on or before August 10th each year. Once the roll is delivered, it is set until the following year.

## Slide 9: The Calendar: Election Dates
Set by Elections Code Section 1500:
  The first Tuesday after the first Monday in May each year.
  The last Tuesday of August each year.
  Any first Tuesday after the first Monday of a month where an election is not otherwise held.

## Slide 10: Elections Administrative Calendar: Important Events
125 Days – Board Resolution Setting the Election (BOS)
120 Days – Publish Notice of Election (Elections Dept.)
109 Days – Last Day to File Arguments
      (Advisory Committees & Interested Parties)
99 Days – Last Day to File Rebuttal Arguments (Advisory Committees & Interested Parties)
15 Days – Last Day to Register to Vote in Election (Voters and Residents)
Election Day – Last Day to Cast Ballot
Actual dates for each election change annually.

## Slide 11: Elections: Arguments for or Against the Measure
Arguments FOR or AGAINST the Measure - 300 words.
Contact Elections to obtain Arguments filed.
Rebuttals to Arguments - 250 words.
Original signatures required on submission to Elections.
Contact the County Elections Department for additional information.
Notes: Arguments are prepared by registered voters who are zone residents. Arguments may be made both for and against a measure; rebuttals may be made to each argument. Original documents with original signatures are required. Contact the Elections office during the argument period to obtain filed arguments.

## Slide 12: March 5th, 2024 Primary Election DEADLINES Calendar: The Board of Supervisors
Board Date: October 24th, 2023
      125 days prior to March 5th, 2024 election is November 1st, 2023.
      No meeting on November 1st, 2023.
      October 24th, 2023 is latest available date to meet 125-day requirement.
Due to CAO October 6th, 2023
      Two weeks prior to Meeting
Due to Chief Fiscal Officer October 3rd, 2023
      Three days prior to CAO
Due to Dept. Director September 28th, 2023
      Five days prior to CFO.
Due to County Counsel September 11th, 2023
      Three weeks prior to Dept. Director
Notes: For the May 7, 2013 Election date, 125 days is January 2, 2013. Due to the holidays, there is no meeting that day, or the preceding week, December 25, 2012. The latest date a meeting is available to schedule the Resolutions is December 18, 2012.

## Slide 13: Timeline for March 2024 Election
August 15th, 2023 – Election request due to DOT for October Board date
October 24th, 2023 – Resolution to Board setting measure for election
November 17th, 2023 – Arguments for and against measure close; Check the County website!
November 24th, 2023 – Last day to file rebuttal arguments; Check the County Website!
February 2024 – Ballots Mailed
March 5th, 2024 – Election Day
Notes: The Advisory Committee needs to allow at least two weeks preparation time and scheduling for the Board Agenda & Resolution.

## Slide 14: November 5TH, 2024 GENERAL Election DEADLINES The Board of Supervisors 2024 calendar is not available until the end of 2023. Example timelines are provided below:
Board Date: June 25th, 2024
      125 days prior to November 5th, 2024 election is July 3rd, 2024.
      No meeting on Wednesday July 3rd, 2024.
      June 25th, 2024 is latest date to meet 125-day requirement.
Due to CAO June 7th, 2024
      Two weeks prior to Meeting
Due to Chief Fiscal Officer June 4th, 2024
      Three days prior to CAO
Due to Dept. Director May 30th, 2024
      Five days prior to CFO.
Due to County Counsel May 6th, 2024
      Three weeks prior to Dept. Director
Notes: For the May 7, 2013 Election date, 125 days is January 2, 2013. Due to the holidays, there is no meeting that day, or the preceding week, December 25, 2012. The latest date a meeting is available to schedule the Resolutions is December 18, 2012.

## Slide 15: Timeline for november 2024 Election
April 1st, 2024 – Election request due to DOT for June Board date
June 25th, 2024– Resolution to Board setting measure for election
July 19th, 2024– Arguments for and against measure close; Check the County website!
July 26th, 2024– Last day to file rebuttal arguments; Check the County Website!
October 2024 – Ballots Mailed
November 5th, 2024 – Election Day
Notes: The Advisory Committee needs to allow at least two weeks preparation time and scheduling for the Board Agenda & Resolution.

## Slide 16: Elections REQUEST DEADLINES:
Election Date
  March 5th, 2024
  November 5th, 2024
Respective request due to County
  August 15th, 2023
  April 1st, 2024
August 10th is the tax roll date!
A special tax approved in an August election will not be on the books until the following year.

## Slide 17: Check List
Notice Meeting with Agenda.
Be clear about the topic in the Agenda Item.
Hold open meeting.
Document discussion, decision and recommendation in minutes.
Deliver recommendation to Zone Administration.
Monitor the County Websites for Updates:
    Board of Supervisors Agenda
    Elections Website
    Zones of Benefit Website